name: j harish anandam                    ex no: 2                                              reg no: 2116241201501

Software Project Plan

Scope, Timeline, and Team Roles for a Sample Application

Sample Application: Library Management System

# Aim

To prepare a software project plan for the development of a Library Management System, covering the project scope, development timeline, and team roles and responsibilities.

# Objective

- Define the scope of the project, including in-scope and out-of-scope items.

- Break down the project into phases with a realistic timeline.

- Identify the team structure and assign roles and responsibilities.

- Identify key deliverables, milestones, and risks for planning purposes.

# Project Overview

| Attribute | Details |
| --- | --- |
| Project Name | Library Management System |
| Project Type | Web-Based Library Automation Application |
| Methodology | Agile (Scrum) with DevOps practices |
| Estimated Duration | 14 Weeks (3 Sprints of 4 weeks each, post-planning) |
| Team Size | 7 Members |

# Project Scope

## In-Scope

- Member registration, login, and profile management

- Book catalog search and browsing by title, author, or category

- Book issue, renewal, and return processing

- Fine calculation for overdue books

- Book reservation and availability notifications

- Librarian module for catalog and inventory management

- Book procurement and stock management

- Admin module for member, staff, and reports/analytics management

- Deployment on cloud/on-premise infrastructure with CI/CD pipeline

## Out-of-Scope

- Inter-library loan / consortium sharing across branches (Phase 2)

- AI-based book recommendation engine (Phase 2)

- E-book and digital lending integration (Phase 2)

- Mobile app version (Phase 2)

## Assumptions and Constraints

- SMS/email notification APIs are available and stable for integration.

- Barcode/RFID scanning hardware is available for book tracking, if required.

- Requirements may evolve; scope changes will be handled through Agile backlog grooming.

- Existing book catalog data will be provided in a digitizable format for migration.

# Project Timeline

The project follows an Agile delivery model with an initial planning phase followed by three development sprints, and a final stabilization and deployment phase.

| Phase | Activities | Duration | Week(s) |
| --- | --- | --- | --- |
| Phase 1: Initiation & Planning | Requirement gathering, feasibility study, project charter, team onboarding | 2 Weeks | Week 1 - 2 |
| Phase 2: Design | System architecture, database design, UI wireframes, API design | 2 Weeks | Week 3 - 4 |
| Sprint 1: Core Modules | Member registration/login, book catalog, search | 2 Weeks | Week 5 - 6 |
| Sprint 2: Circulation | Book issue, renewal, return, fine calculation | 2 Weeks | Week 7 - 8 |
| Sprint 3: Librarian & Admin | Librarian module, procurement, admin module, reports/analytics | 2 Weeks | Week 9 - 10 |
| Phase 3: Testing | Unit, integration, system, and user acceptance testing | 2 Weeks | Week 11 - 12 |
| Phase 4: Deployment & Go-Live | Deployment, data migration, staff training, go-live | 1 Week | Week 13 |
| Phase 5: Maintenance & Support | Bug fixes, performance monitoring, feedback-driven enhancements | 1 Week + | Week 14+ |

## Key Milestones

- M1: Project Charter and Requirement Specification signed off — End of Week 2

- M2: System Design and Database schema approved — End of Week 4

- M3: Book catalog and search functional — End of Week 6

- M4: Circulation (issue/return/fine) module complete — End of Week 8

- M5: Librarian and admin modules complete — End of Week 10

- M6: UAT sign-off and go-live — End of Week 13

# Team Roles and Responsibilities

| Role | Count | Key Responsibilities |
| --- | --- | --- |
| Project Manager / Scrum Master | 1 | Project planning, sprint facilitation, risk management, stakeholder communication |
| Business Analyst | 1 | Requirement gathering, SRS documentation, backlog prioritization with librarians |
| UI/UX Designer | 1 | Wireframes, prototypes, user experience design for staff and member portals |
| Backend Developer | 2 | API development, database design, circulation and fine-calculation logic |
| Frontend Developer | 1 | Web UI development, catalog and member portal screens |
| QA / Test Engineer | 1 | Test planning, unit/integration/UAT testing, defect tracking |

## Reporting Structure

All developers and the QA engineer report to the Project Manager / Scrum Master. The Business Analyst and UI/UX Designer collaborate directly with the Project Manager and with library staff during planning and design phases. Daily stand-ups, sprint planning, and sprint retrospectives are facilitated by the Scrum Master.

# Key Deliverables

- Project Charter and Software Requirement Specification (SRS)

- System Architecture, ER Diagrams, and Database Schema

- Working software increments at the end of each sprint

- Test Plan and Test Case documentation

- Deployment and data migration documentation

- User manuals for librarians, staff, and members

# Risk Management

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Incomplete or inconsistent legacy catalog data | High | Data cleansing and validation during migration; run parallel checks before cutover |
| Scope creep from changing requirements | Medium | Maintain a prioritized backlog; review changes in sprint planning |
| Staff resistance to new system | Medium | Early staff involvement, training sessions, and phased rollout |
| Barcode/RFID hardware compatibility issues | Medium | Validate hardware compatibility early; keep manual entry as fallback |

# Conclusion

This project plan defines a clear scope, a phased 14-week Agile timeline, and a well-structured team of seven members with defined roles and responsibilities for building the Library Management System. Following this plan will help ensure timely delivery, manageable risk, and a high-quality system that meets the needs of library staff and members.